## Product Backlog
Epic ID | User Story ID | User Story Description | Priority | Story Points | Sprint | Acceptance Criteria | Status | Assigned To | Notes
EP-01 | US-01 | As a user, I want to upload PDF documents so the system can index them | High | 5 | Sprint 1 | File accepted and indexed within 5 seconds | Completed | Dev Team | Core feature
EP-01 | US-02 | As a user, I want to upload DOCX documents for text extraction | High | 3 | Sprint 1 | DOCX text extracted and stored | Completed | Dev Team
EP-01 | US-03 | As a user, I want unsupported file types to show an error message | Medium | 2 | Sprint 1 | Error message displayed for TXT/unsupported | Completed | Dev Team
EP-01 | US-04 | As a user, I want large PDF files blocked with a warning | Medium | 2 | Sprint 1 | Files above limit blocked with clear message | Completed | Dev Team
EP-02 | US-05 | As a user, I want to type a natural language query to search documents | High | 8 | Sprint 2 | Relevant documents returned within 2s | Completed | Dev Team | RAG pipeline
EP-02 | US-06 | As a user, I want search results ranked by relevance | High | 5 | Sprint 2 | Top 5 results shown with relevance score | In Progress | Dev Team | FAISS scoring
EP-02 | US-07 | As a user, I want source citations shown with every answer | High | 5 | Sprint 2 | Source filename + page displayed | In Progress | Dev Team
EP-03 | US-08 | As a user, I want a chat interface with multi-turn conversation | High | 8 | Sprint 3 | Follow-up questions understand context | Not Started | Dev Team | Dialogue mgmt
EP-03 | US-09 | As a user, I want conversation history saved per session | Medium | 3 | Sprint 3 | History retrievable within session | Not Started | Dev Team
EP-04 | US-10 | As a user, I want the system deployed on a live URL | High | 5 | Sprint 4 | App accessible on Vercel URL | Not Started | Dev Team | Vercel + Render
EP-04 | US-11 | As a user, I want response times under 3 seconds | Medium | 3 | Sprint 4 | 95% responses under 3s in testing | Not Started | Dev Team | Performance

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
SPRINT 1 BACKLOG
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (in Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 47 | 6 | 7 | 11 | 4 | 3 | 0 | 9 | 9 | 8 | 6 | 8 | 9 | 8
US-01 | T-01 | Design document upload UI | 3/1/2026 | 3/2/2026 | Intern Name | Design | 3- Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-02 | Implement backend API for file upload | 3/2/2026 | 3/4/2026 | Intern Name | Coding | 3- Completed | 8 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-03 | Validate file formats (PDF, DOCX) | 3/4/2026 | 3/4/2026 | Intern Name | Unit Test | 3- Completed | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-04 | Research text extraction libraries | 3/1/2026 | 3/1/2026 | Intern Name | Others | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-05 | Implement PDF text extraction | 3/3/2026 | 3/5/2026 | Intern Name | Coding | 2- In Progress | 10 | 0 | 0 | 3 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-06 | Implement DOCX text extraction | 3/5/2026 | 3/6/2026 | Intern Name | Coding | 1- Not Started | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-07 | Setup basic document indexing structure | 3/6/2026 | 3/7/2026 | Intern Name | Build | 1- Not Started | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-08 | Verify indexed data integrity | 3/7/2026 | 3/7/2026 | Intern Name | Integration Test | 1- Not Started | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-09 | Integrate FAISS vector database | 3/8/2026 | 3/10/2026 | Intern Name | Coding | 2- In Progress | 12 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-10 | Implement embedding model (BAAI/bge) | 3/9/2026 | 3/11/2026 | Intern Name | Coding | 1- Not Started | 10 | 0 | 0 | 0 | 0 | 3 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-11 | Build RAG query pipeline | 3/11/2026 | 3/13/2026 | Intern Name | Coding | 1- Not Started | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0
US-07 | T-12 | Implement source citation in responses | 3/13/2026 | 3/14/2026 | Intern Name | Coding | 1- Not Started | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0

## Stand up Meeting
NOTES: Stand-up should be max 15 minutes. Keep blockers actionable.
Date | Team Member | Yesterday Done | Today Plan | Blockers / Impediments | Action Owner | Resolved (Y/N)
3/1/2026 | Dev Team | Set up project repo, installed dependencies | Design document upload UI wireframes | No blockers | Dev Team | Y
3/2/2026 | Dev Team | Completed upload UI wireframes | Implement backend API for file upload | Need API keys for LLM service | Team Lead | N
3/3/2026 | Dev Team | Backend API 50% complete | Continue API + start PDF extraction | API rate limits unclear | Dev Team | Y
3/4/2026 | Dev Team | Completed file upload API | Validate file formats, start DOCX extraction | DOCX parsing library issue | Dev Team | Y
3/5/2026 | Dev Team | File format validation done | Implement PDF text extraction | pdfplumber version conflict | Dev Team | Y
3/6/2026 | Dev Team | PDF extraction complete | DOCX extraction + indexing structure | No blockers | Dev Team | Y
3/7/2026 | Dev Team | DOCX extraction 80% done | Complete DOCX + verify indexed data | No blockers | Dev Team | Y
3/10/2026 | Dev Team | Sprint 1 complete, Sprint 2 started | Integrate FAISS vector DB | FAISS installation on Render unclear | Team Lead | N
3/11/2026 | Dev Team | FAISS integrated locally | Implement BAAI/bge embedding model | Model download speed slow in prod | Dev Team | Y
3/12/2026 | Dev Team | Embedding model implemented | Build RAG query pipeline | No blockers | Dev Team | Y

## Retrospective
NOTES: Retrospective should focus on process improvements, not blame. Timebox to 60 minutes.
Sprint | Category | What Went Well | What Could Be Improved | Action Item | Owner | Due Date | Status
Sprint 1 | Technical | pdfplumber worked well for text extraction | DOCX extraction took longer than estimated | Spike DOCX libraries before sprint start | Dev Team | 3/8/2026 | Closed
Sprint 1 | Process | Daily standups kept team aligned | Blockers not raised early enough | Add blocker escalation rule to DoD | Team Lead | 3/8/2026 | Closed
Sprint 1 | Technical | File validation logic was clean | No unit tests for edge cases | Write unit tests for all edge cases in Sprint 2 | Dev Team | 3/15/2026 | Open
Sprint 2 | Technical | FAISS integration went smoothly | Model download slow in production | Cache model on Render, pre-load on startup | Dev Team | 3/22/2026 | Open
Sprint 2 | Process | RAG pipeline design was well-architected | LLM API costs not estimated upfront | Add cost estimation to sprint planning | Team Lead | 3/22/2026 | Open
Sprint 2 | Quality | Source citations added value to answers | Relevance ranking needs tuning | Research advanced reranking strategies | Dev Team | 3/29/2026 | Not Started