## Defects
Submitted Date | Defect ID | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Severity | Priority | Remarks
3/5/2026 | DEF-001 | File upload fails for large PDF files (>10MB) | Sprint 1 | Intern Name | Functional | Added file size validation and optimized upload logic | 3/6/2026 | Closed | High | High | Working as expected
3/6/2026 | DEF-002 | Extracted text contains special character issues | Sprint 1 | Intern Name | Data | Implemented text cleanup and encoding fix | 3/7/2026 | Closed | Medium | Medium | Verified with multiple documents
3/7/2026 | DEF-003 | DOCX files not processed correctly for tables | Sprint 1 | Intern Name | Functional | Fixed DOCX parsing logic for nested tables | 3/8/2026 | Closed | High | High | No errors observed
3/8/2026 | DEF-004 | Search results not ranked properly by relevance | Sprint 2 | Intern Name | Performance | Improved relevance scoring logic in FAISS | 3/10/2026 | Open | Medium | High | Needs further tuning
3/9/2026 | DEF-005 | Chatbot response delayed for large document sets | Sprint 2 | Intern Name | Performance | Added basic caching mechanism for repeated queries | 3/11/2026 | Open | High | High | Monitoring performance
3/10/2026 | DEF-006 | UI misalignment on document upload screen (mobile) | Sprint 2 | Intern Name | UI | Corrected CSS styling for responsive layout | 3/10/2026 | Closed | Low | Medium | UI verified on multiple devices
3/11/2026 | DEF-007 | Incorrect error message for unsupported file types | Sprint 2 | Intern Name | Usability | Updated validation messages to be descriptive | 3/12/2026 | Closed | Low | Low | Improved user feedback
3/12/2026 | DEF-008 | Duplicate documents allowed during upload | Sprint 3 | Intern Name | Functional | Added duplicate check using file hash comparison | 3/13/2026 | Closed | Medium | Medium | Duplicate prevention working
3/14/2026 | DEF-009 | Source citations missing for some document chunks | Sprint 3 | Intern Name | Functional | Fixed chunk metadata preservation in RAG pipeline | 3/15/2026 | Open | High | High | Partial fix applied
3/15/2026 | DEF-010 | Multi-turn context lost after 5th query | Sprint 3 | Intern Name | Functional | Increased conversation history buffer size | 3/16/2026 | Open | Medium | High | Needs regression testing
3/17/2026 | DEF-011 | Backend API returns 500 error on empty query | Sprint 4 | Intern Name | Functional | Added input validation and empty query guard | 3/17/2026 | Closed | High | Critical | No further occurrences
3/18/2026 | DEF-012 | Cold start on Render causes 30s timeout | Sprint 4 | Intern Name | Performance | Implemented health-check ping to prevent cold start | 3/19/2026 | Open | Medium | Medium | Monitoring uptime

## Summary
Defect Summary Dashboard
Category | Count
Total Defects | 12
Open Defects | 5
Closed Defects | 7
Critical Severity | 0
High Severity | 5
Medium Severity | 5
Low Severity | 2
Functional Defects | 6
Performance Defects | 3
UI/Usability Defects | 2